## 工作表1
Date | Time | Task | Event
2026-04-18 | 6:15 | C05 | Sailing to F2-C05
2026-04-18 | 8:40 | C05 | Pushing on F2-C05 ; climbing tower
2026-04-18 |  | C05 | set up AIB/current meter；pre-dive check；CP snapshot
2026-04-18 | 9:00 | C05 | AIB launch
2026-04-18 |  | C05 | legC(GVI+Anode)
2026-04-18 | 10:16 | C05 | recovery/change battery
2026-04-18 | 10:28 | C05 | AIB launch
2026-04-18 | 10:34 | C05 | legD(GVI+Anode)
2026-04-18 |  | C05 | FaceAB2(GVI+Anode)
2026-04-18 |  | C05 | CPS1(Mosaic)
2026-04-18 | 12:00 | C05 | recovery/change battery
2026-04-18 | 12:10 | C05 | AIB launch
2026-04-18 | 12:20 | C05 | FaceCD2(GVI+Anode)
2026-04-18 | 12:50 | C05 | recovery
2026-04-18 |  | C05 | CP snapshot
2026-04-18 |  | C05 | Wash down
2026-04-18 |  | C05 | data transform
2026-04-18 | 14:00 | C05 | Pack up instruments and clean the site
2026-04-18 | 14:30 | C05 | Sailing to taichung port
2026-04-18 | 17:10 | C05 | At Port
2026-04-18 | 17:10 | C05 | DPR / Reporting / Admin
2026-04-19 | 6:18 | C05 | Sailing to F2-C05
2026-04-19 | 8:40 | C05 | Pushing on F2-C05 ; climbing tower
2026-04-19 |  | C05 | set up AIB/current meter；pre-dive check；CP snapshot
2026-04-19 | 9:20 | C05 | AIB launch
2026-04-19 |  | C05 | legB(GVI+Anode)
2026-04-19 | 10:40 | C05 | recovery/change battery
2026-04-19 | 11:00 | C05 | AIB launch
2026-04-19 | 11:10 | C05 | legB(Scour+Moasic)
2026-04-19 | 12:10 | C05 | recovery/change battery
2026-04-19 | 12:20 | C05 | AIB launch
2026-04-19 | 12:36 | C05 | FaceAB1(GVI+Anode)
2026-04-19 | 13:10 | C05 | tether tangle with anode
2026-04-19 |  | C05 | try to recovery the AUV
2026-04-19 | 14:48 | C05 | Pack up instruments and clean the site
2026-04-19 | 14:50 | C05 | Sailing to taichung port
2026-04-19 | 17:40 | C05 | At Port
2026-04-19 | 17:40 | C05 | DPR / Reporting / Admin
2026-04-20 | 6:15 | C05 | Sailing to F2-C05
2026-04-20 | 8:22 | C05 | Pushing on F2-C05 ; climbing tower
2026-04-20 |  | C05 | set up AIB-009/current meter；pre-dive check
2026-04-20 | 9:25 | C05 | AIB-009 launch
2026-04-20 |  | C05 | rescue AIB-007
2026-04-20 | 10:28 | C05 | recovery AIB-007
2026-04-20 | 10:36 | C05 | recovery AIB-009
2026-04-20 |  | C05 | wash and maintain AIB-007
2026-04-20 |  | C05 | set up AIB-009；CP snapshot
2026-04-20 | 12:00 | C05 | AIB-009 launch
2026-04-20 |  | C05 | FaceBC1(GVI+Anode)
2026-04-20 |  | C05 | CPS2(Mosaic+GVI+Anode)
2026-04-20 | 12:39 | C05 | recovery/change battery AIB-009
2026-04-20 | 12:40 | C05 | AIB-009 launch
2026-04-20 |  | C05 | legB(Scour+Moasic)
2026-04-20 | 12:50 | C05 | recovery AIB-009
2026-04-20 |  | C05 | maintain
2026-04-20 | 14:12 | C05 | Sailing to taichung port
2026-04-20 | 17:00 | C05 | At Port
2026-04-20 | 17:00 | C05 | DPR / Reporting / Admin
2026-04-21 | 6:06 | C05 | Sailing to F2-C05
2026-04-21 | 8:03 | C05 | Pushing on F2-C05 ; climbing tower
2026-04-21 |  | C05 | set up AIB-009/current meter；pre-dive check
2026-04-21 | 8:40 | C05 | AIB-009 launch
2026-04-21 |  | C05 | FaceBC1(GVI+Anode)
2026-04-21 | 10:28 | C05 | recovery AIB-007
2026-04-21 | 10:36 | C05 | recovery AIB-009
2026-04-21 |  | C05 | wash and maintain AIB-007
2026-04-21 |  | C05 | set up AIB-009；CP snapshot
2026-04-21 | 8:40 | C05 | AIB-009 launch
2026-04-21 |  | C05 | FaceDA1(GVI+Anode)
2026-04-21 |  | C05 | FaceDA2(GVI+Anode)
2026-04-21 | 9:30 | C05 | recovery/change battery AIB-009
2026-04-21 | 9:46 | C05 | AIB-009 launch
2026-04-21 |  | C05 | FaceCD1(GVI+Anode)
2026-04-21 | 11:05 | C05 | recovery AIB-009
2026-04-21 |  | C05 | maintain
2026-04-21 | 12:14 | C05 | data transform
2026-04-21 | 13:10 | C05 | climbing down C05
2026-04-21 |  | C05 | Waiting for B07 taems
2026-04-21 | 14:18 | C05 | Sailing to taichung port
2026-04-21 | 16:40 | C05 | At Port
2026-04-21 | 16:40 | C05 | DPR / Reporting / Admin
2026-04-22 | 6:12 | A02 | Sailing to F2-A02
2026-04-22 | 8:19 | A02 | Pushing on F2-A02 ; climbing tower
2026-04-22 |  | A02 | set up AIB-009/current meter；pre-dive check；lifting bag
2026-04-22 | 8:30 | A02 | AIB-009 launch
2026-04-22 |  | A02 | LegC(GVI+CPM+Scour)
2026-04-22 |  | A02 | LegC(Moasic)
2026-04-22 |  | A02 | FaceBC1(Anode)
2026-04-22 |  | A02 | FaceBC1(GVI+CPM)
2026-04-22 | 10:30 | A02 | recovery AIB-009
2026-04-22 |  | A02 | CP snapshot
2026-04-22 |  | A02 | maintain
2026-04-22 |  | A02 | data transform
2026-04-22 | 11:12 | A02 | climbing down A02
2026-04-22 |  | A02 | Waiting for A03 taems
2026-04-22 | 13:00 | A02 | Sailing to taichung port
2026-04-22 | 15:30 | A02 | At Port
2026-04-22 | 15:30 | A02 | DPR / Reporting / Admin
2026-04-23 | 9:00 | Non-Offshore | Weather Standby.
2026-04-23 | 17:30 | Non-Offshore | DPR
2026-04-24 | 9:00 | Non-Offshore | Weather Standby.
2026-04-24 | 17:30 | Non-Offshore | DPR
2026-04-25 | 9:00 | Non-Offshore | Weather Standby.
2026-04-25 | 17:30 | Non-Offshore | DPR
2026-04-26 | 6:04 | A02 | Sailing to F2-A02
2026-04-26 | 8:25 | A02 | Pushing on F2-A02 ; climbing tower
2026-04-26 |  | A02 | set up AIB-009/current meter；pre-dive check；lifting bag
2026-04-26 | 9:15 | A02 | AIB-009 launch
2026-04-26 |  | A02 | Start operation
2026-04-26 |  | A02 | Leg B Down
2026-04-26 |  | A02 | Leg B GCI
2026-04-26 |  | A02 | Leg B Scour
2026-04-26 | 10:25 | A02 | Recover
2026-04-26 | 10:45 | A02 | Launch
2026-04-26 |  | A02 | Brace B1C
2026-04-26 |  | A02 | Brace D2A
2026-04-26 |  | A02 | Brace A1D
2026-04-26 | 11:15 | A02 | Recover
2026-04-26 | 11:30 | A02 | Launch
2026-04-26 |  | A02 | Leg A Up
2026-04-26 |  | A02 | Leg A Down
2026-04-26 |  | A02 | Leg A GCI
2026-04-26 |  | A02 | Leg A Scour
2026-04-26 | 12:30 | A02 | Recover
2026-04-26 |  | A02 | Maintain
2026-04-26 | 14:10 | A02 | climbing down F2-A02
2026-04-26 |  | A02 | Sailing to taichung port
2026-04-26 | 16:40 | A02 | At Port
2026-04-26 |  | A02 | DPR / Reporting / Admin
2026-04-27 | 6:04 | A02 | Sailing to F2-A02
2026-04-27 | 8:25 | A02 | Pushing on F2-A02 ; climbing tower
2026-04-27 |  | A02 | set up AIB-009/current meter；pre-dive check；lifting bag
2026-04-27 | 8:45 | A02 | AIB-009 launch
2026-04-27 |  | A02 | Start operation
2026-04-27 |  | A02 | Face AB1 & AB2(GVI & CPM & Anode)
2026-04-27 |  | A02 | Leg B (Anode & Boatlanding)
2026-04-27 | 9:35 | A02 | Recover
2026-04-27 | 9:45 | A02 | Launch
2026-04-27 |  | A02 | Face CD1 & CD2 (CVI & CPM)
2026-04-27 | 10:42 | A02 | Recover
2026-04-27 | 10:53 | A02 | Launch
2026-04-27 |  | A02 | CPS2 (GVI & CPM & Mosaic)
2026-04-27 | 11:39 | A02 | Recover
2026-04-27 |  | A02 | Maintan
2026-04-27 | 13:40 | A02 | Climbing down F2-A02
2026-04-27 |  | A02 | Sailing to Taichung port
2026-04-27 | 17:30 | A02 | At port
2026-04-27 | 17:30 | A02 | DPR / Reporting / Admin
2026-04-28 | 6:03 | A02 | Sailing to F2-A02
2026-04-28 | 8:06 | A02 | Pushing on F2-A02 ; climbing tower
2026-04-28 |  | A02 | set up AIB-009/current meter；pre-dive check；lifting bag
2026-04-28 |  | A02 | TBT
2026-04-28 | 8:40 | A02 | AIB-009 launch
2026-04-28 |  | A02 | Leg D (GVI & CPM & Scour & Anode & Mosaic)
2026-04-28 |  | A02 | CPS1 (GVI & CPM & Mosaic)
2026-04-28 | 10:00 | A02 | Recover/change battery AIB-009
2026-04-28 | 10:15 | A02 | AIB-009 launch
2026-04-28 |  | A02 | current to height
2026-04-28 | 10:25 | A02 | Recover AIB-009
2026-04-28 |  | A02 | waiting for low current
2026-04-28 |  | A02 | maintain AIB-007
2026-04-28 | 13:04 | A02 | CP snapshot
2026-04-28 |  | A02 | Maintain and wash down AIB-009
2026-04-28 | 14:02 | A02 | Climbing down F2-A02
2026-04-28 |  | A02 | waiting for B04 teams
2026-04-28 | 14:40 | A02 | Sailing to Taichung port
2026-04-28 | 17:10 | A02 | At port
2026-04-28 | 17:10 | A02 | DPR / Reporting / Admin
2026-04-29 | 6:10 | A02 | Sailing to F2-A02
2026-04-29 | 8:18 | A02 | Pushing on F2-A02 ; climbing tower
2026-04-29 |  | A02 | set up AIB-009/current meter；pre-dive check；lifting bag
2026-04-29 |  | A02 | TBT
2026-04-29 | 9:00 | A02 | AIB-009 launch
2026-04-29 |  | A02 | LegC (Anode )
2026-04-29 |  | A02 | Face DA1 (Anode )
2026-04-29 | 9:15 | A02 | Recover AIB-009
2026-04-29 |  | A02 | maintain AIB-009/house keeping/pack up for transit to A03
2026-04-29 | 10:24 | A02 | climb down A02
2026-04-29 | 10:30 | A02 | reach to A03
2026-04-29 |  | A02 | A03 yo-yo is not suitable to climb
2026-04-29 |  | A02 | waiting for CC permition to A05
2026-04-29 | 11:45 | A02 | climbing A05
2026-04-29 |  | A02 | lift equipment
2026-04-29 |  | A02 | house keeping
2026-04-29 | 12:36 | A02 | Climbing down A05
2026-04-29 |  | A02 | waiting for A06 teams
2026-04-29 | 13:20 | A02 | Sailing to Taichung port
2026-04-29 | 16:02 | A02 | At port
2026-04-29 | 16:02 | A02 | DPR / Reporting / Admin
2026-04-30 | 9:00 | Non-Offshore | data processing
2026-04-30 | 12:00 | Non-Offshore | lunch time
2026-04-30 | 13:00 | Non-Offshore | data processing
2026-04-30 | 18:00 | Non-Offshore | Get off work
2026-05-01 | 9:00 | Non-Offshore | writing report & paper reading
2026-05-01 | 12:00 | Non-Offshore | lunch time
2026-05-01 | 13:00 | Non-Offshore | writing report & paper reading
2026-05-01 | 18:00 | Non-Offshore | Get off work
2026-05-02 | 6:20 | A05 | Sailing to F2-A05
2026-05-02 | 8:37 | A05 | Pushing on F2-A05 ; climbing tower
2026-05-02 |  | A05 | set up AIB-009/current meter；pre-dive check；lifting bag
2026-05-02 |  | A05 | TBT
2026-05-02 | 9:15 | A05 | AIB-009 launch
2026-05-02 |  | A05 | Face BC1 (GVI & CPM & Anode )
2026-05-02 |  | A05 | Face BC2 (GVI & CPM & Anode )
2026-05-02 | 10:45 | A05 | Recover/change battery AIB-009
2026-05-02 |  | A05 | maintain AIB-009/house keeping/pack up for transit to A03
2026-05-02 | 11:00 | A05 | AIB-009 launch
2026-05-02 |  | A05 | Face AB1 (GVI & CPM & Anode )
2026-05-02 |  | A05 | Face AB2 (GVI & CPM & Anode )
2026-05-02 | 12:12 | A05 | Recover/change battery AIB-009
2026-05-02 | 12:27 | A05 | AIB-009 launch
2026-05-02 |  | A05 | LegA (GVI & CPM & scour & mosaic )
2026-05-02 | 12:40 | A05 | Recover AIB-009
2026-05-02 |  | A05 | maintain AIB-009
2026-05-02 |  | A05 | house keeping
2026-05-02 | 12:36 | A05 | Climbing down A05
2026-05-02 |  | A05 | waiting for A03 teams
2026-05-02 | 13:45 | A05 | Sailing to Taichung port
2026-05-02 | 16:18 | A05 | At port
2026-05-02 | 16:18 | A05 | DPR / Reporting / Admin
2026-05-03 | 6:20 | A05 | Sailing to F2-A05
2026-05-03 | 8:35 | A05 | Pushing on F2-A02 ; climbing tower
2026-05-03 |  | A05 | set up AIB-009/current meter；pre-dive check；lifting bag
2026-05-03 |  | A05 | TBT
2026-05-03 | 9:10 | A05 | AIB-009 launch
2026-05-03 |  | A05 | Face DA1 (GVI & CPM & Anode )
2026-05-03 |  | A05 | Face DA2 (GVI & CPM & Anode )
2026-05-03 |  | A05 | LegA (Anode )
2026-05-03 |  | A05 | LegD (GVI & CPM & scour & mosaic )
2026-05-03 | 10:30 | A05 | Recover AIB-009
2026-05-03 |  | A05 | maintain AIB-009
2026-05-03 |  | A05 | house keeping
2026-05-03 | 11:00 | A05 | Climbing down A05
2026-05-03 |  | A05 | waiting for A03 teams
2026-05-03 | 12:10 | A05 | Sailing to Taichung port
2026-05-03 | 14:35 | A05 | At port
2026-05-03 | 14:35 | A05 | DPR / Reporting / Admin
2026-05-04 | 9:00 | Non-Offshore | data processing
2026-05-04 | 12:00 | Non-Offshore | lunch time
2026-05-04 | 13:00 | Non-Offshore | data processing
2026-05-04 | 18:00 | Non-Offshore | Get off work
2026-05-05 | 6:10 | A05 | Sailing to F2-A05
2026-05-05 | 8:30 | A05 | Pushing on F2-A05 ; climbing tower
2026-05-05 |  | A05 | set up AIB-009/current meter；pre-dive check；lifting bag
2026-05-05 |  | A05 | TBT
2026-05-05 | 9:10 | A05 | AIB-009 launch
2026-05-05 |  | A05 | Face CD1 (GVI & CPM & Anode )
2026-05-05 |  | A05 | Face CD2 (GVI & CPM & Anode )
2026-05-05 |  | A05 | LegC (GVI & CPM & Anode & scour & mosaic )
2026-05-05 |  | A05 | LegD (Anode )
2026-05-05 |  | A05 | CPS1(GVI & CPM & mosaic)
2026-05-05 | 10:47 | A05 | Recovery/Change battery AIB-009
2026-05-05 | 11:00 | A05 | AIB-009 launch
2026-05-05 |  | A05 | LegB (GVI & CPM & Anode & scour & mosaic &Boatlanding )
2026-05-05 | 12:15 | A05 | Recovery/Change battery AIB-009
2026-05-05 | 12:35 | A05 | AIB-009 launch
2026-05-05 |  | A05 | CPS2(GVI & CPM & mosaic)-Ali pilot
2026-05-05 | 13:15 | A05 | Recovery AIB-009
2026-05-05 |  | A05 | maintain AIB-009
2026-05-05 |  | A05 | house keeping
2026-05-05 | 14:25 | A05 | Climbing down A05
2026-05-05 |  | A05 | waiting for A03 teams
2026-05-05 | 14:45 | A05 | Sailing to Taichung port
2026-05-05 | 17:20 | A05 | At port
2026-05-05 | 17:20 | A05 | DPR / Reporting / Admin
2026-05-06 | 6:10 | A03 | Sailing to F2-A03
2026-05-06 | 8:31 | A03 | Pushing on F2-A03 ; climbing tower
2026-05-06 |  | A03 | set up AIB-009/current meter；pre-dive check；lifting bag
2026-05-06 |  | A03 | TBT
2026-05-06 | 9:35 | A03 | AIB-009 launch
2026-05-06 |  | A03 | LegA (GVI & CPM )
2026-05-06 |  | A03 | LegB (GVI & CPM )
2026-05-06 |  | A03 | Face AB1 (GVI & CPM & Anode )
2026-05-06 |  | A03 | Face AB2 (GVI & CPM & Anode )
2026-05-06 | 10:25 | A03 | Recovery AIB-009
2026-05-06 |  | A03 | house keeping
2026-05-06 | 13:05 | A03 | Climbing down A03
2026-05-06 |  | A03 | waiting for crew
2026-05-06 | 11:20 | A03 | Sailing to Taichung port
2026-05-06 | 13:40 | A03 | At port
2026-05-06 | 13:40 | A03 | DPR / Reporting / Admin
2026-05-11 | 6:10 | C07 | Sailing to F2-C07
2026-05-11 | 8:34 | C07 | Pushing on F2-C07 ; climbing tower
2026-05-11 |  | C07 | set up AIB-009/current meter；pre-dive check；lifting bag
2026-05-11 |  | C07 | Bi Weekly Maintain
2026-05-11 |  | C07 | TBT
2026-05-11 | 9:55 | C07 | AIB-009 launch
2026-05-11 |  | C07 | Face AB1 (GVI & CPM & Anode )
2026-05-11 |  | C07 | Face AB2 (GVI & CPM & Anode )
2026-05-11 | 10:29 | C07 | Recovery/Change battery AIB-009
2026-05-11 |  | C07 | fix connect error
2026-05-11 | 11:15 | C07 | AIB-009 launch
2026-05-11 |  | C07 | Face CD2 (GVI & CPM & Anode )
2026-05-11 |  | C07 | Face DA2 (GVI & CPM & Anode )
2026-05-11 | 11:40 | C07 | Recovery/Change battery AIB-009
2026-05-11 | 11:47 | C07 | AIB-009 launch
2026-05-11 |  | C07 | Face BC2 (GVI & CPM & Anode )
2026-05-11 | 12:30 | C07 | Recovery/Change battery AIB-009
2026-05-11 | 12:35 | C07 | AIB-009 launch
2026-05-11 |  | C07 | LegA (GVI+CPM & Anode & scour & mosaic )
2026-05-11 | 13:27 | C07 | Recovery AIB-009
2026-05-11 |  | C07 | house keeping
2026-05-11 | 14:40 | C07 | Climbing down C07
2026-05-11 | 14:50 | C07 | Sailing to Taichung port
2026-05-11 | 16:55 | C07 | At port
2026-05-11 | 16:55 | C07 | DPR / Reporting / Admin
2026-05-12 | 6:31 | C07 | Sailing to F2-C07
2026-05-12 | 8:25 | C07 | Pushing on F2-C07 ; climbing tower
2026-05-12 |  | C07 | set up AIB-009/current meter；pre-dive check；lifting bag
2026-05-12 | 9:00 | C07 | F2 HSE Drill
2026-05-12 | 10:00 | C07 | BeeX emergency recovery Drill
2026-05-12 | 11:50 | C07 | WOW
2026-05-12 | 12:35 | C07 | pre-dive test/change battery
2026-05-12 | 12:50 | C07 | AIB-009 launch
2026-05-12 |  | C07 | Face BC1 (GVI & CPM & Anode )
2026-05-12 |  | C07 | LegB (GVI+CPM)
2026-05-12 | 10:29 | C07 | Recovery/Change battery AIB-009
2026-05-12 |  | C07 | Face CD2 (GVI & CPM & Anode )
2026-05-12 |  | C07 | Face DA2 (GVI & CPM & Anode )
2026-05-12 | 13:40 | C07 | Recovery/Change battery AIB-009
2026-05-12 | 13:50 | C07 | AIB-009 launch
2026-05-12 |  | C07 | Face DA1 (GVI & CPM & Anode )
2026-05-12 |  | C07 | LegD (GVI+CPM & scour & mosaic)
2026-05-12 | 14:40 | C07 | Recovery AIB-009
2026-05-12 |  | C07 | house keeping
2026-05-12 | 15:10 | C07 | Climbing down C07
2026-05-12 |  | C07 | wait for C05 teams
2026-05-12 | 15:40 | C07 | Sailing to Taichung port
2026-05-12 | 17:45 | C07 | At port
2026-05-12 | 17:45 | C07 | DPR / Reporting / Admin
2026-05-13 | 6:10 | C07 | Sailing to F2-C07
2026-05-13 | 8:04 | C07 | Pushing on F2-C07 ; climbing tower
2026-05-13 |  | C07 | set up AIB-009/current meter；pre-dive check；lifting bag
2026-05-13 | 8:50 | C07 | AIB-009 launch
2026-05-13 |  | C07 | Face CD1 (GVI & CPM & Anode )
2026-05-13 |  | C07 | LegC (GVI+CPM)
2026-05-13 | 9:30 | C07 | Recovery/Change battery AIB-009
2026-05-13 |  | C07 | WOW
2026-05-13 | 1:30 | C07 | maintain AIB-009
2026-05-13 |  | C07 | house keeping
2026-05-13 | 2:06 | C07 | Climbing down C07
2026-05-13 |  | C07 | wait for C01 teams
2026-05-13 | 16:00 | C07 | Sailing to Taichung port
2026-05-13 | 18:20 | C07 | At port
2026-05-13 | 18:20 | C07 | DPR / Reporting / Admin
2026-05-14 | 6:10 | C07 | Sailing to F2-C07
2026-05-14 | 8:13 | C07 | lightning alert
2026-05-14 |  | C07 | WOW
2026-05-14 | 10:20 | C07 | Mission canceled
2026-05-14 | 10:35 | C07 | Sailing to Taichung port
2026-05-14 | 13:00 | C07 | At port
2026-05-14 |  | C07 | data processing
2026-05-14 | 14:00 | C07 | DPR / Reporting / Admin
2026-05-15 | 6:18 | C07 | Sailing to F2-C07
2026-05-15 | 8:20 | C07 | Pushing on F2-C07 ; climbing tower
2026-05-15 |  | C07 | set up AIB-009/current meter；pre-dive check；lifting bag
2026-05-15 | 8:52 | C07 | AIB-009 launch
2026-05-15 |  | C07 | LegD (Anode)
2026-05-15 |  | C07 | CPS1(GVI+CPM & mosaic)
2026-05-15 | 9:30 | C07 | Recovery/Change battery AIB-009
2026-05-15 | 9:40 | C07 | AIB-009 launch
2026-05-15 |  | C07 | LegC (Anode & scour & mosaic)
2026-05-15 |  | C07 | CPS2(GVI+CPM & mosaic)
2026-05-15 | 10:30 | C07 | Recovery/Change battery AIB-009
2026-05-15 |  | C07 | WoW
2026-05-15 | 12:00 | C07 | maintain AIB-009
2026-05-15 |  | C07 | house keeping
2026-05-15 | 12:40 | C07 | Climbing down C07
2026-05-15 |  | C07 | wait for C08 teams
2026-05-15 | 13:30 | C07 | Sailing to Taichung port
2026-05-15 | 16:05 | C07 | at port
2026-05-15 | 16:05 | C07 | DPR / Reporting / Admin
2026-05-16 | 9:00 | Non-Offshore | data processing
2026-05-16 | 12:00 | Non-Offshore | lunch time
2026-05-16 | 13:00 | Non-Offshore | data processing
2026-05-16 | 18:00 | Non-Offshore | Get off work
2026-05-17 | 6:10 | C07 | Sailing to F2-C07
2026-05-17 | 6:50 | C07 | high waves
2026-05-17 |  | C07 | Sailing to Taichung port
2026-05-17 | 8:00 | C07 | at port
2026-05-17 |  | C07 | DPR / Reporting / Admin
2026-05-18 | 6:05 | C07 | Sailing to F2-C07
2026-05-18 | 8:02 | C07 | Pushing on F2-C07 ; climbing tower
2026-05-18 |  | C07 | set up AIB-009/current meter；pre-dive check；lifting bag
2026-05-18 | 8:38 | C07 | AIB-009 launch
2026-05-18 |  | C07 | LegB (Anode & scour & mosaic & Boatlanding)
2026-05-18 | 9:40 | C07 | Recovery/Change battery AIB-009
2026-05-18 |  | C07 | maintain AIB-009
2026-05-18 |  | C07 | house keeping
2026-05-18 | 10:40 | C07 | climbing down C07
2026-05-18 | 10:50 | C07 | Pushing on F2-C08 ; climbing tower
2026-05-18 |  | C07 | set up AIB-009/current meter；pre-dive check；lifting bag
2026-05-18 |  | C07 | WOW
2026-05-18 | 12:00 | C07 | maintain AIB-009
2026-05-18 |  | C07 | house keeping
2026-05-18 | 13:20 | C07 | Climbing down C08
2026-05-18 |  | C07 | wait for C10 teams
2026-05-18 | 14:40 | C07 | Sailing to Taichung port
2026-05-18 | 17:00 | C07 | at port
2026-05-18 | 17:00 | C07 | DPR / Reporting / Admin
2026-05-19 | 6:12 | C08 | Sailing to F2-C08
2026-05-19 | 8:14 | C08 | Pushing on F2-C11
2026-05-19 |  | C08 | wait team C11
2026-05-19 | 8:37 | C08 | Pushing on F2-C08
2026-05-19 |  | C08 | set up AIB-009/current meter；pre-dive check；lifting bag
2026-05-19 | 9:20 | C08 | AIB-009 launch
2026-05-19 |  | C08 | Face AB1(GVI+CPM & Anode)
2026-05-19 |  | C08 | Face AB2(GVI+CPM & Anode)
2026-05-19 | 10:00 | C08 | Recovery/Change battery AIB-009
2026-05-19 | 10:10 | C08 | AIB-009 launch
2026-05-19 |  | C08 | Face AB3(GVI+CPM & Anode)
2026-05-19 | 10:50 | C08 | Recovery/Change battery AIB-009
2026-05-19 | 11:00 | C08 | AIB-009 launch
2026-05-19 |  | C08 | Face DA1(GVI+CPM )
2026-05-19 |  | C08 | Face DA2(GVI+CPM )
2026-05-19 |  | C08 | Face DA3(GVI+CPM )
2026-05-19 |  | C08 | LegD(GVI+CPM )
2026-05-19 | 11:36 | C08 | Recovery AIB-009
2026-05-19 |  | C08 | Wow
2026-05-19 | 13:00 | C08 | maintain AIB-009
2026-05-19 |  | C08 | house keeping
2026-05-19 | 13:50 | C08 | Climbing down C08
2026-05-19 |  | C08 | wait for C02 teams
2026-05-19 | 14:20 | C08 | Sailing to Taichung port
2026-05-19 | 16:50 | C08 | at port
2026-05-19 | 16:50 | C08 | DPR / Reporting / Admin
2026-05-20 | 6:10 | C08 | Sailing to F2-C08
2026-05-20 | 8:05 | C08 | Pushing on F2-C08
2026-05-20 | 8:30 | C08 | AIB-009 launch
2026-05-20 |  | C08 | Face DA1(Anode)
2026-05-20 |  | C08 | Face DA2(Anode)
2026-05-20 |  | C08 | Face DA3(Anode)
2026-05-20 |  | C08 | LegA(GVI+CPM & Anode & scour & mosaic)
2026-05-20 | 9:40 | C08 | Recovery/Change battery AIB-009
2026-05-20 | 9:50 | C08 | AIB-009 launch
2026-05-20 |  | C08 | Face CD1(GVI+CPM )
2026-05-20 |  | C08 | Face CD2(GVI+CPM )
2026-05-20 |  | C08 | LegC(GVI+CPM & Anode & scour & mosaic )
2026-05-20 | 11:05 | C08 | Recovery/Change battery AIB-009
2026-05-20 |  | C08 | WOW
2026-05-20 | 12:20 | C08 | maintain AIB-009
2026-05-20 |  | C08 | house keeping
2026-05-20 | 12:45 | C08 | Climbing down C08
2026-05-20 |  | C08 | wait for C05 teams
2026-05-20 | 14:25 | C08 | Sailing to Taichung port
2026-05-20 | 17:00 | C08 | at port
2026-05-20 | 17:00 | C08 | DPR / Reporting / Admin
2026-05-21 | 6:00 | C08 | Sailing to F2-C08
2026-05-21 | 8:05 | C08 | Pushing on F2-C08
2026-05-21 | 8:30 | C08 | WOW
2026-05-21 | 11:30 | C08 | AIB-009 launch
2026-05-21 |  | C08 | LegD (Anode / Scour / Mosaic)
2026-05-21 |  | C08 | Face CD3 (GVI / CPM)
2026-05-21 |  | C08 | CPS2 (GVI / CPM / Mosaic)
2026-05-21 | 12:30 | C08 | Recovery AIB-009
2026-05-21 |  | C08 | maintain AIB-009
2026-05-21 |  | C08 | house keeping
2026-05-21 | 13:30 | C08 | Climbing down C08
2026-05-21 |  | C08 | Sailing to Taichung port
2026-05-21 | 16:40 | C08 | at port
2026-05-21 |  | C08 | DPR / Reporting / Admin
2026-05-22 | 6:00 | C08 | Waiting for another team to lift the equipment onto the vessel.
2026-05-22 | 6:50 | C08 | Sailing to F2-C08
2026-05-22 | 8:55 | C08 | Pushing on F2-C08
2026-05-22 | 9:30 | C08 | AIB-009 launch
2026-05-22 |  | C08 | Face CD1 (Anode)
2026-05-22 |  | C08 | Face CD2 (Anode)
2026-05-22 |  | C08 | CPS1 (GVI / CPM / Mosaic)
2026-05-22 | 10:25 | C08 | Recovery/Change battery AIB-009
2026-05-22 | 10:30 | C08 | AIB-009 launch
2026-05-22 |  | C08 | Face CD1 (Anode)
2026-05-22 |  | C08 | Face CD2 (Anode)
2026-05-22 | 11:15 | C08 | Recovery/Change battery AIB-009
2026-05-22 | 11:20 | C08 | AIB-009 launch
2026-05-22 |  | C08 | Face BC1 (GVI / CPM / Anode)
2026-05-22 |  | C08 | Face BC2 (GVI / CPM / Anode)
2026-05-22 | 12:00 | C08 | Recovery/Change battery AIB-009
2026-05-22 | 12:20 | C08 | AIB-009 launch
2026-05-22 |  | C08 | LegD (GVI / CPM / Anode / Scour / Boatlanding / Mosaic)
2026-05-22 | 13:20 | C08 | Recovery AIB-009
2026-05-22 |  | C08 | maintain AIB-009
2026-05-22 |  | C08 | house keeping
2026-05-22 | 14:30 | C08 | Climbing down C08
2026-05-22 |  | C08 | Waiting for the other team
2026-05-22 |  | C08 | Sailing to Taichung port
2026-05-22 | 18:25 | C08 | at port
2026-05-22 |  | C08 | DPR / Reporting / Admin
2026-05-23 | 6:00 | C08 | Waiting for the crew to make preparations.
2026-05-23 | 6:40 | C08 | Sailing to F2-C08
2026-05-23 | 9:20 | C08 | Pushing on F2-C08
2026-05-23 |  | C08 | Pack all equipment and proceed with lifting operations.
2026-05-23 | 10:00 | C08 | Climbing down C08
2026-05-23 |  | C08 | Sailing to C07
2026-05-23 | 10:20 | C08 | Pushing on F2-C07
2026-05-23 |  | C08 | Lifting all equipment and proceed with setup and installation.
2026-05-23 | 11:45 | C08 | AIB-009 launch
2026-05-23 |  | C08 | The current was strong
2026-05-23 | 11:53 | C08 | Recovery AIB-009
2026-05-23 |  | C08 | maintain AIB-009
2026-05-23 |  | C08 | house keeping
2026-05-23 | 13:15 | C08 | Climbing down C07
2026-05-23 |  | C08 | Waiting for the other team
2026-05-23 |  | C08 | Sailing to Taichung port
2026-05-23 | 17:10 | C08 | at port
2026-05-23 |  | C08 | DPR / Reporting / Admin
2026-05-24 | 6:00 | C07 | Waiting for another team to lift the equipment onto the vessel.
2026-05-24 | 6:18 | C07 | Sailing to F2-C07
2026-05-24 | 8:20 | C07 | Pushing on F2-C07
2026-05-24 |  | C07 | set up AIB-009/current meter；pre-dive check；lifting bag
2026-05-24 | 8:50 | C07 | AIB-009 launch
2026-05-24 |  | C07 | LegB (Re-do scour)
2026-05-24 | 9:17 | C07 | Recovery AIB-009
2026-05-24 |  | C07 | maintain AIB-009
2026-05-24 |  | C07 | Pack all equipment and proceed with lifting operations.
2026-05-24 | 10:45 | C07 | Climbing down C07
2026-05-24 |  | C07 | Waiting for the other team
2026-05-24 |  | C07 | Sailing to Taichung port
2026-05-24 | 16:45 | C07 | at port
2026-05-24 |  | C07 | DPR / Reporting / Admin
2026-05-25 | 6:12 | D03 | Sailing to F2
2026-05-25 | 8:10 | D03 | try to push on F2-D03
2026-05-25 |  | D03 | The mission was canceled due to a large fishing net.
2026-05-25 |  | D03 | Waiting for team C02
2026-05-25 | 10:20 | D03 | Sailing to Taichung port
2026-05-25 | 12:45 | D03 | at port
2026-05-25 |  | D03 | DPR / Reporting / Admin
2026-05-26 | 9:00 | Non-Offshore | writing report & paper reading
2026-05-26 | 12:00 | Non-Offshore | lunch time
2026-05-26 | 13:00 | Non-Offshore | writing report & paper reading
2026-05-26 | 18:00 | Non-Offshore | Get off work
2026-05-27 | 9:00 | Non-Offshore | writing report & paper reading
2026-05-27 | 12:00 | Non-Offshore | lunch time
2026-05-27 | 13:00 | Non-Offshore | writing report & paper reading
2026-05-27 | 18:00 | Non-Offshore | Get off work
2026-05-28 | 9:00 | Non-Offshore | writing report & paper reading
2026-05-28 | 12:00 | Non-Offshore | lunch time
2026-05-28 | 13:00 | Non-Offshore | writing report & paper reading
2026-05-28 | 18:00 | Non-Offshore | Get off work
2026-05-29 | 9:00 | Non-Offshore | data processing
2026-05-29 | 12:00 | Non-Offshore | lunch time
2026-05-29 | 13:00 | Non-Offshore | data processing
2026-05-29 | 18:00 | Non-Offshore | Get off work
2026-05-30 | 9:00 | Non-Offshore | writing report & paper reading
2026-05-30 | 12:00 | Non-Offshore | lunch time
2026-05-30 | 13:00 | Non-Offshore | writing report & paper reading
2026-05-30 | 18:00 | Non-Offshore | Get off work
2026-05-31 | 9:00 | Non-Offshore | writing report & paper reading
2026-05-31 | 12:00 | Non-Offshore | lunch time
2026-05-31 | 13:00 | Non-Offshore | writing report & paper reading
2026-05-31 | 18:00 | Non-Offshore | Get off work
2026-06-01 | 6:00 | D10 | Sailing to F2-D10
2026-06-01 | 7:55 | D10 | Pushing on F2-D10
2026-06-01 |  | D10 | crane issue
2026-06-01 | 8:23 | D10 | climb down D10
2026-06-01 |  | D10 | Waiting for OCC permit before proceeding with D11.
2026-06-01 | 6:00 | D11 | Sailing to F2-D10
2026-06-01 | 7:55 | D11 | Pushing on F2-D10
2026-06-01 |  | D11 | crane issue
2026-06-01 | 8:23 | D11 | climb down D10
2026-06-01 |  | D11 | Waiting for OCC permit before proceeding with D11.
2026-06-01 | 9:12 | D11 | Pushing on F2-D11
2026-06-01 |  | D11 | current meter/set up AIB-009
2026-06-01 | 10:25 | D11 | AIB-009 launch
2026-06-01 |  | D11 | Face AB1(GVI & Anode)
2026-06-01 |  | D11 | Face AB2(GVI & Anode)
2026-06-01 |  | D11 | Face AB3(GVI & Anode)
2026-06-01 | 11:04 | D11 | Recovery/Change battery AIB-009
2026-06-01 | 11:08 | D11 | AIB-009 launch
2026-06-01 |  | D11 | Face AD1(GVI & Anode)
2026-06-01 |  | D11 | Face AD2(GVI & Anode)
2026-06-01 |  | D11 | Face AD3(GVI & Anode)
2026-06-01 |  | D11 | LegA(GVI & Anode & scour & mosaic )
2026-06-01 | 12:20 | D11 | Recovery AIB-009
2026-06-01 |  | D11 | maintain AIB-009
2026-06-01 |  | D11 | house keeping
2026-06-01 | 13:30 | D11 | Climbing down C08
2026-06-01 |  | D11 | Sailing to Taichung port
2026-06-01 | 15:30 | D11 | at port
2026-06-01 |  | D11 | DPR / Reporting / Admin
2026-06-02 | 6:05 | D11 | Sailing to F2-D11
2026-06-02 | 7:50 | D11 | Pushing on F2-D11
2026-06-02 |  | D11 | current meter/set up AIB-009
2026-06-02 | 8:30 | D11 | AIB-009 launch
2026-06-02 |  | D11 | Face BC1(GVI & Anode)
2026-06-02 |  | D11 | Face BC2(GVI & Anode)
2026-06-02 |  | D11 | Face BC3(GVI)
2026-06-02 |  | D11 | Face CD1(GVI & Anode)
2026-06-02 |  | D11 | Face CD2(GVI & Anode)
2026-06-02 |  | D11 | Face CD3(GVI)
2026-06-02 | 9:40 | D11 | Recovery/Change battery AIB-009
2026-06-02 | 9:44 | D11 | AIB-009 launch
2026-06-02 |  | D11 | LegD(GVI & Anode & scour & mosaic )
2026-06-02 |  | D11 | CPS-D(GVI & mosaic )
2026-06-02 |  | D11 | LegC(GVI & Anode & scour & mosaic )
2026-06-02 |  | D11 | CPS-C(GVI & mosaic )
2026-06-02 | 11:40 | D11 | Recovery/Change battery AIB-009
2026-06-02 | 11:48 | D11 | AIB-009 launch
2026-06-02 |  | D11 | legB
2026-06-02 | 12:00 | D11 | Recovery
2026-06-02 |  | D11 | maintain AIB-009
2026-06-02 |  | D11 | house keeping
2026-06-02 | 13:05 | D11 | Climbing down D11
2026-06-02 |  | D11 | Sailing to Taichung port
2026-06-02 | 15:30 | D11 | at port
2026-06-02 |  | D11 | DPR / Reporting / Admin
2026-06-03 | 6:00 | D11 | Sailing to F2-D11
2026-06-03 | 7:45 | D11 | Pushing on F2-D11
2026-06-03 |  | D11 | current meter/set up AIB-009
2026-06-03 | 8:32 | D11 | AIB-009 launch
2026-06-03 |  | D11 | LegB(GVI & Anode & scour & mosaic & Boat Landing )
2026-06-03 | 9:25 | D11 | RecoveryAIB-009
2026-06-03 |  | D11 | Troubleshooting the software.
2026-06-03 |  | D11 | maintain AIB-009
2026-06-03 |  | D11 | house keeping
2026-06-03 | 11:30 | D11 | Climbing down D11
2026-06-03 |  | D11 | Sailing to Taichung port
2026-06-03 | 13:40 | D11 | at port
2026-06-03 |  | D11 | DPR / Reporting / Admin
2026-06-04 | 6:00 | D09 | Sailing to F2-D09
2026-06-04 | 8:00 | D09 | Pushing on F2-D09
2026-06-04 |  | D09 | current meter/set up AIB-009
2026-06-04 | 8:45 | D09 | WOW
2026-06-04 | 10:59 | D09 | AIB-009 launch
2026-06-04 | 11:10 | D09 | RecoveryAIB-009
2026-06-04 |  | D09 | maintain AIB-009
2026-06-04 |  | D09 | house keeping
2026-06-04 | 12:26 | D09 | Climbing down D09
2026-06-04 |  | D09 | Sailing to Taichung port
2026-06-04 | 14:55 | D09 | at port
2026-06-04 |  | D09 | DPR / Reporting / Admin
2026-06-05 | 6:00 | D09 | Sailing to F2-D09
2026-06-05 | 8:00 | D09 | Pushing on F2-D09
2026-06-05 |  | D09 | current meter/set up AIB-009
2026-06-05 | 8:25 | D09 | WOW
2026-06-05 | 11:45 | D09 | maintain AIB-009
2026-06-05 |  | D09 | house keeping
2026-06-05 | 12:15 | D09 | Climbing down D09
2026-06-05 |  | D09 | Sailing to Taichung port
2026-06-05 | 14:35 | D09 | at port
2026-06-05 |  | D09 | DPR / Reporting / Admin
2026-06-06 | 6:00 | D09 | Sailing to F2-D09
2026-06-06 | 6:39 | D09 | Returned to port due to poor weather conditions.
2026-06-06 | 7:15 | D09 | at port
2026-06-06 |  | D09 | DPR / Reporting / Admin
2026-06-06 |  | D09 | Awaiting schedule updates.
2026-06-07 | 9:00 | Non-Offshore | WOW
2026-06-07 | 17:30 | Non-Offshore | DPR / Reporting / Admin
2026-06-08 | 6:10 | D09 | Sailing to F2-D09
2026-06-08 | 8:03 | D09 | Pushing on F2-D09
2026-06-08 |  | D09 | current meter/set up AIB-009
2026-06-08 | 8:35 | D09 | strong current
2026-06-08 |  | D09 | maintain AIB-009
2026-06-08 | 10:00 | D09 | WOW
2026-06-08 |  | D09 | house keeping
2026-06-08 | 1:00 | D09 | Climbing down D11
2026-06-08 |  | D09 | Sailing to Taichung port
2026-06-08 | 15:15 | D09 | at port
2026-06-08 |  | D09 | DPR / Reporting / Admin
2026-06-09 | 9:00 | Non-Offshore | writing report & paper reading
2026-06-09 | 12:00 | Non-Offshore | lunch time
2026-06-09 | 13:00 | Non-Offshore | writing report & paper reading
2026-06-09 | 18:00 | Non-Offshore | Get off work
2026-06-10 | 9:00 | Non-Offshore | writing report & paper reading
2026-06-10 | 12:00 | Non-Offshore | lunch time
2026-06-10 | 13:00 | Non-Offshore | writing report & paper reading
2026-06-10 | 18:00 | Non-Offshore | Get off work
2026-06-11 | 6:10 | D09 | Sailing to F2-D09
2026-06-11 | 7:10 | D09 | high wave
2026-06-11 | 7:10 | D09 | Sailing to Taichung port
2026-06-11 | 8:10 | D09 | at port
2026-06-11 |  | D09 | DPR / Reporting / Admin
2026-06-12 | 6:10 | D09 | Sailing to F2-D09
2026-06-12 | 8:01 | D09 | Pushing on F2-D09
2026-06-12 |  | D09 | current meter/set up AIB-009
2026-06-12 | 8:30 | D09 | strong current
2026-06-12 |  | D09 | maintain AIB-009 / Imenco
2026-06-12 | 10:00 | D09 | WOW
2026-06-12 |  | D09 | house keeping
2026-06-12 | 12:55 | D09 | Climbing down D11
2026-06-12 |  | D09 | Wait for A01 and C05 teams
2026-06-12 | 14:40 | D09 | Sailing to Taichung port
2026-06-12 | 17:00 | D09 | at port
2026-06-12 |  | D09 | DPR / Reporting / Admin
2026-06-13 | 9:00 | Non-Offshore | writing report & paper reading
2026-06-13 | 12:00 | Non-Offshore | lunch time
2026-06-13 | 13:00 | Non-Offshore | writing report & paper reading
2026-06-13 | 18:00 | Non-Offshore | Get off work
2026-06-14 | 9:00 | Non-Offshore | Data processing
2026-06-14 | 12:00 | Non-Offshore | lunch time
2026-06-14 | 13:00 | Non-Offshore | Data processing
2026-06-14 | 18:00 | Non-Offshore | Get off work
2026-06-15 | 9:00 | Non-Offshore | writing report & paper reading
2026-06-15 | 12:00 | Non-Offshore | lunch time
2026-06-15 | 13:00 | Non-Offshore | writing report & paper reading
2026-06-15 | 18:00 | Non-Offshore | Get off work
2026-06-16 | 9:00 | Non-Offshore | writing report & paper reading
2026-06-16 | 12:00 | Non-Offshore | lunch time
2026-06-16 | 13:00 | Non-Offshore | writing report & paper reading
2026-06-16 | 18:00 | Non-Offshore | Get off work
2026-06-17 | 9:00 | Non-Offshore | writing report & paper reading
2026-06-17 | 12:00 | Non-Offshore | lunch time
2026-06-17 | 13:00 | Non-Offshore | writing report & paper reading
2026-06-17 | 18:00 | Non-Offshore | Get off work
2026-09-13 | 5:10 | D06 | Lifting equipment onto the CTV
2026-09-13 | 5:35 | D06 | sail to F2
2026-09-13 | 7:40 | D06 | Attempted to push on at D-06, but failed.
2026-09-13 | 7:50 | D06 | Attempted to push on at D-11, but failed.
2026-09-13 |  | D06 | Captain and Site Supervisor decided to cancel today's mission.
2026-09-13 | 8:00 | D06 | Sailed back to Taichung Port.
2026-09-13 | 10:30 | D06 | at port
2026-09-13 |  | D06 | DPR / Reporting / Admin
2026-09-14 | 9:00 | Non-Offshore | writing report & paper reading
2026-09-14 | 12:00 | Non-Offshore | lunch time
2026-09-14 | 13:00 | Non-Offshore | writing report & paper reading
2026-09-14 | 18:00 | Non-Offshore | Get off work
2026-09-15 | 9:00 | Non-Offshore | battery maintenance
2026-09-15 | 9:30 | Non-Offshore | Tether reel maintenance
2026-09-15 | 10:00 | Non-Offshore | Comprehensive test on the vehicle (thrusters, main hull, navigation hull, fairings, etc.)
2026-09-15 | 11:00 | Non-Offshore | Comprehensive test on equipment(topside box, battery charge box)
2026-09-15 | 12:00 | Non-Offshore | have lunch and take a small rest
2026-09-15 | 13:00 | Non-Offshore | Pre-dive test
2026-09-15 | 14:00 | Non-Offshore | CP Calibration & Basic Troubleshooting
2026-09-15 | 16:00 | Non-Offshore | AIB flight simulation – GVI (Leg Down & Leg Up, Brace, Scour, and Mosaic)
2026-09-16 | 9:00 | Non-Offshore | transfer the equipment
2026-09-16 | 9:30 | Non-Offshore | Introdution on AIB
2026-09-16 | 10:00 | Non-Offshore | Connect vehicle/pre dive test/cp calibration
2026-09-16 | 11:00 | Non-Offshore | Launch AIB
2026-09-16 | 12:00 | Non-Offshore | have lunch and take a small rest
2026-09-16 | 13:00 | Non-Offshore | Pilot training:Basic moving(waypoint&manual)
2026-09-16 | 14:00 | Non-Offshore | Pilot training:pile inspection
2026-09-16 | 16:00 | Non-Offshore | Tetherline
2026-09-16 | 17:00 | Non-Offshore | lesson learn
2026-09-17 | 6:20 | D06 | sail to F2
2026-09-17 | 7:20 | D06 | strong current
2026-09-17 |  | D06 | Captain and Site Supervisor decided to cancel today's mission.
2026-09-17 |  | D06 | Sailed back to Taichung Port.
2026-09-17 | 8:30 | D06 | at port
2026-09-17 |  | D06 | DPR / Reporting / Admin
2026-09-18 | 6:20 | D05 | sail to F2
2026-09-18 | 7:20 | D05 | strong current
2026-09-18 |  | D05 | Attempted to push on at D05, but failed.
2026-09-18 |  | D05 | Sailed to D08(seasight team)
2026-09-18 | 8:00 | D05 | Attempted to push on at D08, but failed.
2026-09-18 |  | D05 | Sailed to A01(F2 team)
2026-09-18 | 8:20 | D05 | push on A01
2026-09-18 |  | D05 | Standby, waiting for the F2 team to complete their work.
2026-09-18 | 8:50 | D05 | sail to D11(seasight team)
2026-09-18 | 9:25 | D05 | Attempted to push on at D11, but failed.
2026-09-18 | 9:30 | D05 | Sailed back to Taichung Port.
2026-09-18 | 11:40 | D05 | at port
2026-09-18 |  | D05 | DPR / Reporting / Admin
2026-09-19 | 5:09 | C09 | sail to F2-C09
2026-09-19 |  | C09 | strong current and big wave,the boat's speed is only about 8 knots.
2026-09-19 | 9:50 | C09 | Pushing on F2-C09
2026-09-19 |  | C09 | current meter/set up AIB-009
2026-09-19 | 10:25 | C09 | WOW
2026-09-19 | 10:58 | C09 | AIB-009 launch
2026-09-19 |  | C09 | LegA(GVI& Anode & scour & mosaic )
2026-09-19 | 11:45 | C09 | RecoveryAIB-009
2026-09-19 |  | C09 | maintain AIB-009
2026-09-19 |  | C09 | house keeping
2026-09-19 | 12:30 | C09 | Waiting for Vesse
2026-09-19 | 13:14 | C09 | Climbing down D09
2026-09-19 |  | C09 | Sailing to Taichung port
2026-09-19 | 16:00 | C09 | at port
2026-09-19 |  | C09 | DPR / Reporting / Admin
2026-09-20 | 6:05 | C09 | sail to F2-C09
2026-09-20 | 8:28 | C09 | Pushing on F2-C09
2026-09-20 |  | C09 | current meter/set up AIB-009
2026-09-20 | 9:16 | C09 | AIB-009 launch,but failed and Tetherline damaged and needs to be replaced
2026-09-20 | 9:25 | C09 | Replace Tetherline
2026-09-20 | 10:00 | C09 | AIB-009 launch
2026-09-20 |  | C09 | Face DA1.2.3(GVI & Anode )
2026-09-20 | 11:04 | C09 | RecoveryAIB-009
2026-09-20 |  | C09 | maintain AIB-009
2026-09-20 |  | C09 | house keeping
2026-09-20 | 11:40 | C09 | Climbing down D09
2026-09-20 |  | C09 | Sailing to Taichung port
2026-09-20 | 14:00 | C09 | at port
2026-09-20 |  | C09 | DPR / Reporting / Admin
2026-09-21 | 6:35 | C09 | sail to F2-C09
2026-09-21 | 9:05 | C09 | Pushing on F2-C09,but failed
2026-09-21 |  | C09 | WOW
2026-09-21 | 9:33 | C09 | The weather conditions at the site remain unstable, so we are returning to port.
2026-09-21 |  | C09 | Sailing to Taichung port
2026-09-21 | 12:00 | C09 | at port
2026-09-21 |  | C09 | DPR / Reporting / Admin
2026-09-22 | 6:35 | C09 | sail to F2-C09
2026-09-22 | 7:00 | C09 | strong current
2026-09-22 |  | C09 | Captain and Site Supervisor decided to cancel today's mission.
2026-09-22 |  | C09 | Sailed back to Taichung Port.
2026-09-22 | 7:45 | C09 | at port
2026-09-22 |  | C09 | DPR / Reporting / Admin
2026-09-23 | 9:00 | Non-Offshore | writing report & paper reading
2026-09-23 | 12:00 | Non-Offshore | lunch time
2026-09-23 | 13:00 | Non-Offshore | writing report & paper reading
2026-09-23 | 18:00 | Non-Offshore | Get off work
2026-09-24 | 6:23 | C09 | Sail to F2-C09.
2026-09-24 | 8:40 | C09 | Pushing on F2-C09.
2026-09-24 | 8:47 | C09 | Take out and disassembly AIB to start maintence sequence.
2026-09-24 | 11:51 | C09 | Housekeeping and lunch time.
2026-09-24 | 12:30 | C09 | Wait for vessel.
2026-09-24 | 13:01 | C09 | Climb down F2-C09.
2026-09-24 | 13:09 | C09 | Sail to pick out other teams and back to Taichung Port.
2026-09-24 | 16:36 | C09 | Arrived at Taichung Port.
2026-09-24 |  | C09 | DPR / Reporting / Admin
2026-09-25 | 6:22 | D05 | sail to F2
2026-09-25 | 8:35 | D05 | push on D05
2026-09-25 |  | D05 | climb up D05
2026-09-25 | 9:10 | D05 | set up AIB-006, current meter, pre dive check
2026-09-25 | 9:36 | D05 | launch AIB-006
2026-09-25 |  | D05 | Brace D2A(GVI+CPM+Anode)
2026-09-25 |  | D05 | Brace A1D(GVI+CPM+Anode)
2026-09-25 |  | D05 | Brace D1A(GVI+CPM+Anode)
2026-09-25 |  | D05 | Brace A2D(GVI+CPM+Anode)
2026-09-25 | 10:50 | D05 | recovery AIB-006
2026-09-25 |  | D05 | change battery
2026-09-25 | 11:07 | D05 | launch AIB-006
2026-09-25 |  | D05 | some problem about AIB diving (strong current)
2026-09-25 |  | D05 | current peak up
2026-09-25 | 11:46 | D05 | recovery AIB-006
2026-09-25 |  | D05 | wait for weather
2026-09-25 |  | D05 | data trsnsfer
2026-09-25 |  | D05 | house keeping
2026-09-25 | 14:21 | D05 | sail back to taichung port
2026-09-25 | 16:25 | D05 | at port
2026-09-25 |  | D05 | DPR
2026-09-26 | 6:09 | D05 | sail to F2
2026-09-26 | 8:01 | D05 | push on D05
2026-09-26 | 8:09 | D05 | climb up D05
2026-09-26 |  | D05 | set up AIB-006, current meter, pre dive check
2026-09-26 | 8:48 | D05 | launch AIB-006
2026-09-26 |  | D05 | Brace A3B(GVI+CPM+Anode)
2026-09-26 |  | D05 | Brace B2A(GVI+CPM+Anode)
2026-09-26 | 9:42 | D05 | recovery AIB-006
2026-09-26 |  | D05 | change battery
2026-09-26 | 9:54 | D05 | wait on current
2026-09-26 | 10:14 | D05 | launch AIB-006
2026-09-26 |  | D05 | Brace C3D(GVI+CPM+Anode)
2026-09-26 |  | D05 | Brace D2C(GVI+CPM+Anode)
2026-09-26 | 10:39 | D05 | OCC come in, contact for temporary shutdown
2026-09-26 | 10:48 | D05 | recovery AIB-006
2026-09-26 | 11:41 | D05 | D05 power recovered
2026-09-26 |  | D05 | confirm with OCC
2026-09-26 | 11:57 | D05 | wait on current
2026-09-26 |  | D05 | current keep going up, 0.6~0.8m/s
2026-09-26 | 13:38 | D05 | data transfer, wash down, housekeeping
2026-09-26 | 14:26 | D05 | climb down D05
2026-09-26 | 14:37 | D05 | sail to Taichung Port
2026-09-26 | 16:51 | D05 | at port
2026-09-26 |  | D05 | DPR
2026-09-27 | 6:25 | D05 | sail to F2
2026-09-27 | 8:14 | D05 | push on D05
2026-09-27 |  | D05 | climb up D05
2026-09-27 |  | D05 | set up AIB-006, current meter, pre dive check
2026-09-27 | 8:44 | D05 | launch AIB-006 at west side
2026-09-27 |  | D05 | Brace B3C, C2B, B1C(GVI+CPM+Anode)
2026-09-27 | 10:26 | D05 | recovery AIB-006
2026-09-27 |  | D05 | change battery
2026-09-27 | 10:32 | D05 | wait on current
2026-09-27 | 10:56 | D05 | launch AIB-006 at west side
2026-09-27 |  | D05 | strong swell current
2026-09-27 | 11:19 | D05 | recovery AIB-006
2026-09-27 |  | D05 | AIB check
2026-09-27 |  | D05 | wait on current
2026-09-27 | 13:02 | D05 | data transfer, wash down, housekeeping
2026-09-27 | 13:53 | D05 | climb down D05
2026-09-27 | 14:00 | D05 | sail to Taichung Port
2026-09-27 | 16:19 | D05 | at port
2026-09-27 |  | D05 | DPR
2026-09-28 | 6:10 | D05 | sail to F2
2026-09-28 | 8:00 | D05 | push on D05
2026-09-28 |  | D05 | climb up D05
2026-09-28 |  | D05 | set up AIB-006, current meter, pre dive check
2026-09-28 | 8:36 | D05 | launch AIB-006 at west side
2026-09-28 |  | D05 | C1B, Leg C (GVI+CPM+Anode)
2026-09-28 | 10:05 | D05 | recovery AIB-006
2026-09-28 |  | D05 | change battery
2026-09-28 | 10:22 | D05 | launch AIB-006 at west side
2026-09-28 |  | D05 | D1C, C1D, leg C (GVI+CPM+Anode), Scouring
2026-09-28 | 11:45 | D05 | recovery AIB-006
2026-09-28 |  | D05 | change battery
2026-09-28 | 11:52 | D05 | launch AIB-006 at west side
2026-09-28 |  | D05 | stroung current
2026-09-28 | 12:19 | D05 | recovery AIB-006
2026-09-28 |  | D05 | wait on current
2026-09-28 | 12:49 | D05 | data transfer, wash down, housekeeping
2026-09-28 | 14:08 | D05 | climb down D05
2026-09-28 | 14:10 | D05 | sail to Taichung Port
2026-09-28 | 16:25 | D05 | at port
2026-09-28 |  | D05 | DPR
2026-09-28 | 6:10 | C09 | sail to F2
2026-09-28 | 8:00 | C09 | push on D05
2026-09-28 |  | C09 | D05 team climb(BeeX & Michael)
2026-09-28 | 8:20 | C09 | sail to C09
2026-09-28 | 8:35 | C09 | push on C09
2026-09-28 |  | C09 | climb tower
2026-09-28 | 8:50 | C09 | set up AIB-009, current meter
2026-09-28 | 9:20 | C09 | wait for weather(strong current)
2026-09-28 | 9:30 | C09 | lauch AIB-009
2026-09-28 |  | C09 | Brace C2D(GVI+CPM+Anode)
2026-09-28 |  | C09 | Brace D1C(GVI+CPM+Anode)
2026-09-28 |  | C09 | Brace C1D(GVI+CPM+Anode)
2026-09-28 |  | C09 | Brace D2C(GVI+CPM+Anode)
2026-09-28 | 11:00 | C09 | recovery AIB-009
2026-09-28 |  | C09 | change battery
2026-09-28 | 11:10 | C09 | Leg C(GVI+CPM+Anode+scour+mosaic)
2026-09-28 | 12:10 | C09 | recovery AIB-009
2026-09-28 |  | C09 | wait for weather(strong current)
2026-09-28 | 12:40 | C09 | data transfer
2026-09-28 |  | C09 | house keeping
2026-09-28 | 13:10 | C09 | climb down C09
2026-09-28 | 13:30 | C09 | sail to D05
2026-09-28 | 13:50 | C09 | wait D05 team
2026-09-28 | 14:10 | C09 | sail back taichung port
2026-09-28 | 16:25 | C09 | at port
2026-09-28 |  | C09 | DPR
2026-09-29 | 6:26 | C09 | sail to F2
2026-09-29 | 8:15 | C09 | push on D05
2026-09-29 |  | C09 | D05 team climb(BeeX & Michael)
2026-09-29 | 8:34 | C09 | sail to C09
2026-09-29 | 8:50 | C09 | push on C09
2026-09-29 |  | C09 | clim tower
2026-09-29 | 9:00 | C09 | set up AIB-009, current meter, pre dive check
2026-09-29 | 9:40 | C09 | lauch AIB-009
2026-09-29 |  | C09 | Brace B2C(GVI+CPM+Anode)
2026-09-29 |  | C09 | Brace C1B(GVI+CPM+Anode)
2026-09-29 |  | C09 | Brace B1C(GVI+CPM+Anode)
2026-09-29 |  | C09 | Brace C2B(GVI+CPM+Anode)
2026-09-29 | 11:00 | C09 | recovery AIB-009
2026-09-29 |  | C09 | change battery
2026-09-29 | 11:15 | C09 | lauch AIB-009
2026-09-29 |  | C09 | Leg D(GVI+CPM+Anode+Scour+Mosaic)
2026-09-29 |  | C09 | LegC - CPS
2026-09-29 | 12:40 | C09 | recovery AIB-009
2026-09-29 |  | C09 | data transfer
2026-09-29 |  | C09 | house keeping
2026-09-29 | 13:10 | C09 | climb down C09
2026-09-29 | 13:20 | C09 | sail to D05
2026-09-29 | 13:36 | C09 | wait D05 team
2026-09-29 | 14:00 | C09 | sail back taichung port
2026-09-29 | 16:20 | C09 | at port
2026-09-29 |  | C09 | DPR
2026-09-29 | 6:26 | D05 | sail to F2
2026-09-29 | 8:15 | D05 | push on D05
2026-09-29 |  | D05 | climb up D05
2026-09-29 |  | D05 | set up AIB-006, current meter, pre dive check
2026-09-29 | 9:06 | D05 | launch AIB-006
2026-09-29 |  | D05 | A1B, B1A, Leg B(GVI+CPM+Anode)
2026-09-29 | 10:06 | D05 | recovery AIB-006
2026-09-29 |  | D05 | change battery
2026-09-29 | 10:22 | D05 | launch AIB-006
2026-09-29 |  | D05 | Leg B, CPS(GVI+CPM+Anode)
2026-09-29 | 11:48 | D05 | recovery AIB-006
2026-09-29 |  | D05 | change battery
2026-09-29 | 12:04 | D05 | launch AIB-006
2026-09-29 |  | D05 | Leg B, Boatlanding(GVI+CPM+Anode)
2026-09-29 | 13:11 | D05 | recovery AIB-006
2026-09-29 |  | D05 | data transfer, wash down, housekeeping
2026-09-29 | 13:57 | D05 | climb down D05
2026-09-29 | 14:00 | D05 | sail to Taichung Port
2026-09-29 | 16:20 | D05 | at port
2026-09-29 |  | D05 | DPR
2026-09-30 | 6:10 | C09 | sail to F2
2026-09-30 | 8:00 | C09 | push on D03
2026-09-30 |  | C09 | D03 team climb(vento)
2026-09-30 | 8:35 | C09 | sail to C09
2026-09-30 | 8:47 | C09 | push on C09
2026-09-30 |  | C09 | clim tower
2026-09-30 | 9:00 | C09 | set up AIB-009, current meter, pre dive check
2026-09-30 | 9:30 | C09 | lauch AIB-009
2026-09-30 |  | C09 | Brace A2B(GVI+CPM+Anode)
2026-09-30 |  | C09 | Brace B1A(GVI+CPM+Anode)
2026-09-30 |  | C09 | Brace A1B(GVI+CPM+Anode)
2026-09-30 |  | C09 | Brace B2A(GVI+CPM+Anode)
2026-09-30 | 11:00 | C09 | recovery AIB-009
2026-09-30 |  | C09 | change battery
2026-09-30 | 11:10 | C09 | lauch AIB-009
2026-09-30 |  | C09 | Leg B(GVI+CPM+Anode+Scour+Mosaic+Boatlanding)
2026-09-30 |  | C09 | LegB - CPS
2026-09-30 | 12:40 | C09 | recovery AIB-009
2026-09-30 |  | C09 | data transfer
2026-09-30 |  | C09 | house keeping
2026-09-30 | 14:00 | C09 | climb down C09
2026-09-30 | 14:15 | C09 | sail back taichung port
2026-09-30 | 16:40 | C09 | at port
2026-09-30 |  | C09 | DPR
2026-10-01 | 6:27 | D05 | sail to F2
2026-10-01 | 8:10 | D05 | push on D11
2026-10-01 |  | D05 | D11 team climb(seasight)
2026-10-01 | 8:37 | D05 | sail to C09
2026-10-01 | 8:40 | D05 | push on D05
2026-10-01 |  | D05 | clim tower
2026-10-01 | 9:00 | D05 | set up AIB-006, current meter, pre dive check
2026-10-01 | 9:30 | D05 | lauch AIB-006
2026-10-01 |  | D05 | Leg B(GVI+CPM+Anode+Scour+Mosaic)
2026-10-01 |  | D05 | Leg A(GVI+CPM+Anode+Scour+Mosaic)
2026-10-01 | 10:30 | D05 | recovery AIB-006/fishing net entangled with the thruster
2026-10-01 |  | D05 | change battery
2026-10-01 | 11:00 | D05 | lauch AIB-006
2026-10-01 |  | D05 | LegD (GVI+CPM+Anode+Scour+Mosaic+Boatlanding)
2026-10-01 |  | D05 | LegD - CPS
2026-10-01 | 12:40 | D05 | recovery AIB-006
2026-10-01 |  | D05 | data transfer
2026-10-01 |  | D05 | house keeping
2026-10-01 | 14:10 | D05 | climb down D05
2026-10-01 | 14:25 | D05 | sail to D11
2026-10-01 | 14:30 | D05 | wait D11 team
2026-10-01 | 14:45 | D05 | sail back taichung port
2026-10-01 | 16:50 | D05 | at port
2026-10-01 |  | D05 | DPR
2026-10-02 | 6:20 | D12 | sail to F2
2026-10-02 | 8:08 | D12 | try to push on D12(failed)
2026-10-02 | 8:20 | D12 | Waiting for OCC to cancel today's mission.
2026-10-02 |  | D12 | cancel today's mission.
2026-10-02 | 8:27 | D12 | sail back taichung port
2026-10-02 | 10:35 | D12 | at port
2026-10-02 |  | D12 | DPR
2026-10-02 | 6:20 | D08 | sail to F2
2026-10-02 | 8:08 | D08 | try to push on D12(failed)
2026-10-02 | 8:20 | D08 | Waiting for OCC to cancel today's mission.
2026-10-02 |  | D08 | cancel today's mission.
2026-10-02 | 8:27 | D08 | sail back taichung port
2026-10-02 | 10:35 | D08 | at port
2026-10-02 |  | D08 | DPR
2026-10-03 | 9:00 | Non-Offshore | writing report & paper reading
2026-10-03 | 12:00 | Non-Offshore | lunch time
2026-10-03 | 13:00 | Non-Offshore | writing report & paper reading
2026-10-03 | 18:00 | Non-Offshore | Get off work
2026-10-04 | 9:00 | Non-Offshore | writing report & paper reading
2026-10-04 | 12:00 | Non-Offshore | lunch time
2026-10-04 | 13:00 | Non-Offshore | writing report & paper reading
2026-10-04 | 18:00 | Non-Offshore | Get off work
2026-10-05 | 9:00 | Non-Offshore | writing report & paper reading
2026-10-05 | 12:00 | Non-Offshore | lunch time
2026-10-05 | 13:00 | Non-Offshore | writing report & paper reading
2026-10-05 | 18:00 | Non-Offshore | Get off work
2026-10-06 | 9:00 | Non-Offshore | writing report & paper reading
2026-10-06 | 12:00 | Non-Offshore | lunch time
2026-10-06 | 13:00 | Non-Offshore | writing report & paper reading
2026-10-06 | 18:00 | Non-Offshore | Get off work
2026-10-07 | 9:00 | Non-Offshore | writing report & paper reading
2026-10-07 | 12:00 | Non-Offshore | lunch time
2026-10-07 | 13:00 | Non-Offshore | writing report & paper reading
2026-10-07 | 18:00 | Non-Offshore | Get off work
2026-10-13 | 5:58 | D12 | sail to F2
2026-10-13 | 7:48 | D12 | push on D12
2026-10-13 |  | D12 | climb D12
2026-10-13 | 8:18 | D12 | set up AIB-009, current meter, pre dive check
2026-10-13 | 8:42 | D12 | launch AIB-009
2026-10-13 |  | D12 | leg-A MGM
2026-10-13 | 9:50 | D12 | recovery
2026-10-13 |  | D12 | data transfer
2026-10-13 |  | D12 | house keeping
2026-10-13 | 11:10 | D12 | climb down D12
2026-10-13 | 11:20 | D12 | sail to D08
2026-10-13 | 11:30 | D12 | wait D08 team
2026-10-13 | 11:50 | D12 | sail back taichung port
2026-10-13 | 13:50 | D12 | at port
2026-10-13 |  | D12 | DPR