## 工作表1
Task | Progress | Cluster | Date | Operation | Category | Supervisor | Pilot | Tether Manager | Assistant | Remark
Mobilization | 0% |  | 2026-04-06 | offshore | Mob | Dil | Iqbal | Aiman
C05 | 60.98% | 1 | 2026-04-18 | offshore | Inspection | Dil | Iqbal | Aiman | Ali
C05 | 75.61% | 1 | 2026-04-19 | offshore | Inspection | Dil | Aiman | Iqbal | Ali | Tether entanglement at anode
C05 | 85.37% | 1 | 2026-04-20 | offshore | Inspection | Dil | Aiman | Iqbal | Ali | AIB-007 successfully recovered
C05 | 100% | 1 | 2026-04-21 | offshore | Inspection | Dil | Aiman | Iqbal | Ali
A02 | 15.79% | 1 | 2026-04-22 | offshore | Inspection | Dil | Iqbal | Aiman | Ali
Non-Offshore | 0% |  | 2026-04-23 | onshore | WOW(onshore) | Dil |  |  | David | Weather limit
Non-Offshore | 0% |  | 2026-04-24 | onshore | WOW(onshore) | Dil |  |  | David | Weather limit
Non-Offshore | 0% |  | 2026-04-25 | onshore | WOW(onshore) | Dil |  |  | David | Weather limit
A02 | 44.74% | 1 | 2026-04-26 | offshore | Inspection | Dil | Iqbal | Aiman | David
A02 | 72.97% | 1 | 2026-04-27 | offshore | Inspection | Dil | Iqbal | Aiman | David
A02 | 89.19% | 1 | 2026-04-28 | offshore | Inspection | Dil | Iqbal | Ali
A02 | 94.59% | 1 | 2026-04-29 | offshore | Inspection | Dil | Iqbal | Ali |  | Yo-yo at A03 unsuitable for climbing
Non-Offshore | 0% |  | 2026-04-30 | onshore | Data Processing | Dil |  |  | Ali | Weather limit
Non-Offshore | 0% |  | 2026-05-01 | onshore | WOW(onshore) | Dil |  |  | Ali | Weather limit
A05 | 29.73% | 5 | 2026-05-02 | offshore | Inspection | Dil | Iqbal | Ali
A05 | 51.35% | 5 | 2026-05-03 | offshore | Inspection | Dil | Iqbal | Ali |  | Offshore work limited to half-day due to weather conditions
Non-Offshore | 0% |  | 2026-05-04 | onshore | Data Processing | Dil |  |  | Ali | Weather limit
A05 | 100% | 5 | 2026-05-05 | offshore | Inspection | Dil | Iqbal | Ali
A03 | 16.22% | 5 | 2026-05-06 | offshore | Inspection | Dil | Iqbal | Ali
Non-Offshore | 0% |  | 2026-05-07 | onshore | Day off | Dil |  |  |  | Day off(IOG)
Non-Offshore | 0% |  | 2026-05-08 | onshore | Day off | Dil |  |  |  | Day off(IOG)
Non-Offshore | 0% |  | 2026-05-09 | onshore | Day off | Dil |  |  |  | Day off(IOG)
Non-Offshore | 0% |  | 2026-05-10 | onshore | Day off | Dil |  |  |  | Day off(IOG)
C07 | 37.84% | 4 | 2026-05-11 | offshore | Inspection | Dil | Iqbal | Fremmy | Ali
C07 | 59.46% | 4 | 2026-05-12 | offshore | Inspection | Dil | Iqbal | Fremmy | Ali | F2 HSE Drill/BeeX emergency recovery Drill
C07 | 67.57% | 4 | 2026-05-13 | offshore | Inspection | Dil | Iqbal | Fremmy | Ali
C07 | 67.57% | 4 | 2026-05-14 | offshore | WOW(offshore) | Dil | Iqbal | Fremmy | Ali | OCC canceled today's mission due to lightning alert
C07 | 89.19% | 4 | 2026-05-15 | offshore | Inspection | Dil | Iqbal | Fremmy | Ali
Non-Offshore | 0% |  | 2026-05-16 | onshore | Data Processing | Dil |  |  | Ali | Weather limit
C07 | 89.19% | 4 | 2026-05-17 | offshore | WOW(offshore) | Dil | Iqbal | Fremmy | Ali | OCC canceled today's mission due to high wave
C07 | 100% | 4 | 2026-05-18 | offshore | Inspection | Dil | Iqbal | Fremmy | Ali
C08 | 24.39% | 3 | 2026-05-19 | offshore | Inspection | Dil | Iqbal | Fremmy | Ali
C08 | 60.98% | 3 | 2026-05-20 | offshore | Inspection | Dil | Iqbal | Fremmy | Ali
C08 | 69.05% | 3 | 2026-05-21 | offshore | Inspection | Dil | Iqbal | Fremmy | David
C08 | 100% | 3 | 2026-05-22 | offshore | Inspection | Dil | Iqbal | Fremmy | David
C08 | 100% | 3 | 2026-05-23 | offshore | Inspection | Dil | Iqbal | Fremmy | David
C07 | 100% | 4 | 2026-05-24 | offshore | Inspection | Dil | Iqbal | Fremmy | David | LegB (Re-do scour)
D03 | 0% | 3 | 2026-05-25 | offshore | WOW(offshore) | Dil | Iqbal | Fremmy | Ali | D03 landing obstructed by ~50 m fishing net, CTV unable to proceed. Weather worsening after 10:00, return to Taichung Port before 10:00 per captain.
Non-Offshore | 0% |  | 2026-05-26 | onshore | Day off | Dil |  |  | Ali | Day off(BeeX)
Non-Offshore | 0% |  | 2026-05-27 | onshore | Day off | Dil |  |  | Ali | Day off(BeeX)
Non-Offshore | 0% |  | 2026-05-28 | onshore | Day off | Dil |  |  | Ali | Day off(BeeX)
Non-Offshore | 0% |  | 2026-05-29 | onshore | Data Processing | Dil |  |  | Ali | Weather limit
Non-Offshore | 0% |  | 2026-05-30 | onshore | WOW(onshore) | Dil |  |  | Ali | Weather limit
Non-Offshore | 0% |  | 2026-05-31 | onshore | WOW(onshore) | Dil |  |  | Ali | Weather limit
D10 | 0% | 1 | 2026-06-01 | offshore | Inspection | Dil | Fremmy | Ali |  | D10 crane issue we change to D11.
D11 | 37.21% | 1 | 2026-06-01 | offshore | Inspection | Dil | Fremmy | Ali |  | D10 crane issue we change to D11.
D11 | 88.37% | 1 | 2026-06-02 | offshore | Inspection | Dil | Fremmy | Ali
D11 | 100% | 1 | 2026-06-03 | offshore | Inspection | Dil | Fremmy | Ali
D09 | 0% | 1 | 2026-06-04 | offshore | Inspection | Dil | Fremmy | David |  | strong current
D09 | 0% | 1 | 2026-06-05 | offshore | Inspection | Dil | Fremmy | David |  | strong current
D09 | 0% | 1 | 2026-06-06 | offshore | WOW(offshore) | Dil | Fremmy | David |  | bad weather
Non-Offshore | 0% |  | 2026-06-07 | onshore | WOW(onshore) | Dil |  |  | David | Weather limit
D09 | 0% | 1 | 2026-06-08 | offshore | Inspection | Dil | Fremmy | Ali |  | strong current
Non-Offshore | 0% |  | 2026-06-09 | onshore | WOW(onshore) | Dil |  |  | Ali | Weather limit
Non-Offshore | 0% |  | 2026-06-10 | onshore | WOW(onshore) | Dil |  |  | Ali | Weather limit
D09 | 0% | 1 | 2026-06-11 | offshore | WOW(offshore) | Dil | Iqbal | Fremmy | Ali | OCC canceled today's mission due to high wave
D09 | 0% | 1 | 2026-06-12 | offshore | Inspection | Iqbal | Fremmy | Ali |  | strong current
Non-Offshore | 0% |  | 2026-06-13 | onshore | WOW(onshore) | Iqbal |  |  | Ali | Weather limit
Non-Offshore | 0% |  | 2026-06-14 | onshore | Data Processing | Iqbal |  |  | Ali | Weather limit
Non-Offshore | 0% |  | 2026-06-15 | onshore | WOW(onshore) | Iqbal |  |  | Ali | Weather limit
Non-Offshore | 0% |  | 2026-06-16 | onshore | WOW(onshore) | Iqbal |  |  | Ali | Weather limit
Non-Offshore | 0% |  | 2026-06-17 | onshore | Delay | Iqbal |  |  | Ali | Technical issues with crane operation
Non-Offshore | 0% |  | 2026-06-18 | onshore | Delay | Iqbal |  |  | David | Technical issues with crane operation
Demobilization | 0% |  | 2026-06-19 | offshore | Demob | Iqbal
Standby | 0% |  | 2026-06-20 | onshore | Standby
Standby | 0% |  | 2026-06-21 | onshore | Standby
Standby | 0% |  | 2026-06-22 | onshore | Standby
Standby | 0% |  | 2026-06-23 | onshore | Standby
Standby | 0% |  | 2026-06-24 | onshore | Standby
Standby | 0% |  | 2026-06-25 | onshore | Standby
Standby | 0% |  | 2026-06-26 | onshore | Standby
Standby | 0% |  | 2026-06-27 | onshore | Standby
Standby | 0% |  | 2026-06-28 | onshore | Standby
Standby | 0% |  | 2026-06-29 | onshore | Standby
Standby | 0% |  | 2026-06-30 | onshore | Standby
Standby | 0% |  | 2026-07-01 | onshore | Standby
Standby | 0% |  | 2026-07-02 | onshore | Standby
Standby | 0% |  | 2026-07-03 | onshore | Standby
Standby | 0% |  | 2026-07-04 | onshore | Standby
Standby | 0% |  | 2026-07-05 | onshore | Standby
Standby | 0% |  | 2026-07-06 | onshore | Standby
Standby | 0% |  | 2026-07-07 | onshore | Standby
Standby | 0% |  | 2026-07-08 | onshore | Standby
Standby | 0% |  | 2026-07-09 | onshore | Standby
Standby | 0% |  | 2026-07-10 | onshore | Standby
Standby | 0% |  | 2026-07-11 | onshore | Standby
Standby | 0% |  | 2026-07-12 | onshore | Standby
Standby | 0% |  | 2026-07-13 | onshore | Standby
Standby | 0% |  | 2026-07-14 | onshore | Standby
Standby | 0% |  | 2026-07-15 | onshore | Standby
Standby | 0% |  | 2026-07-16 | onshore | Standby
Standby | 0% |  | 2026-07-17 | onshore | Standby
Standby | 0% |  | 2026-07-18 | onshore | Standby
Standby | 0% |  | 2026-07-19 | onshore | Standby
Standby | 0% |  | 2026-07-20 | onshore | Standby
Standby | 0% |  | 2026-07-21 | onshore | Standby
Standby | 0% |  | 2026-07-22 | onshore | Standby
Standby | 0% |  | 2026-07-23 | onshore | Standby
Standby | 0% |  | 2026-07-24 | onshore | Standby
Standby | 0% |  | 2026-07-25 | onshore | Standby
Standby | 0% |  | 2026-07-26 | onshore | Standby
Standby | 0% |  | 2026-07-27 | onshore | Standby
Standby | 0% |  | 2026-07-28 | onshore | Standby
Standby | 0% |  | 2026-07-29 | onshore | Standby
Standby | 0% |  | 2026-07-30 | onshore | Standby
Standby | 0% |  | 2026-07-31 | onshore | Standby
Standby | 0% |  | 2026-08-01 | onshore | Standby
Standby | 0% |  | 2026-08-02 | onshore | Standby
Standby | 0% |  | 2026-08-03 | onshore | Standby
Standby | 0% |  | 2026-08-04 | onshore | Standby
Standby | 0% |  | 2026-08-05 | onshore | Standby
Standby | 0% |  | 2026-08-06 | onshore | Standby
Standby | 0% |  | 2026-08-07 | onshore | Standby
Standby | 0% |  | 2026-08-08 | onshore | Standby
Standby | 0% |  | 2026-08-09 | onshore | Standby
Standby | 0% |  | 2026-08-10 | onshore | Standby
Standby | 0% |  | 2026-08-11 | onshore | Standby
Standby | 0% |  | 2026-08-12 | onshore | Standby
Standby | 0% |  | 2026-08-13 | onshore | Standby
Standby | 0% |  | 2026-08-14 | onshore | Standby
Standby | 0% |  | 2026-08-15 | onshore | Standby
Standby | 0% |  | 2026-08-16 | onshore | Standby
Standby | 0% |  | 2026-08-17 | onshore | Standby
Standby | 0% |  | 2026-08-18 | onshore | Standby
Standby | 0% |  | 2026-08-19 | onshore | Standby
Standby | 0% |  | 2026-08-20 | onshore | Standby
Standby | 0% |  | 2026-08-21 | onshore | Standby
Standby | 0% |  | 2026-08-22 | onshore | Standby
Standby | 0% |  | 2026-08-23 | onshore | Standby
Standby | 0% |  | 2026-08-24 | onshore | Standby
Standby | 0% |  | 2026-08-25 | onshore | Standby
Standby | 0% |  | 2026-08-26 | onshore | Standby
Standby | 0% |  | 2026-08-27 | onshore | Standby
Standby | 0% |  | 2026-08-28 | onshore | Standby
Standby | 0% |  | 2026-08-29 | onshore | Standby
Standby | 0% |  | 2026-08-30 | onshore | Standby
Standby | 0% |  | 2026-08-31 | onshore | Standby
Standby | 0% |  | 2026-09-01 | onshore | Standby
Standby | 0% |  | 2026-09-02 | onshore | Standby
Standby | 0% |  | 2026-09-03 | onshore | Standby
Standby | 0% |  | 2026-09-04 | onshore | Standby
Standby | 0% |  | 2026-09-05 | onshore | Standby
Standby | 0% |  | 2026-09-06 | onshore | Standby
Standby | 0% |  | 2026-09-07 | onshore | Standby
Standby | 0% |  | 2026-09-08 | onshore | Standby
Standby | 0% |  | 2026-09-09 | onshore | Standby
Standby | 0% |  | 2026-09-10 | onshore | Standby
Standby | 0% |  | 2026-09-11 | onshore | Standby
Standby | 0% |  | 2026-09-12 | onshore | Standby
D06 | 0% | 1 | 2026-09-13 | offshore | WOW(offshore) | Asyraf | Fremmy |  | Ali | Strong current. CTV unable to push on
Non-Offshore | 0% |  | 2026-09-14 | onshore | WOW(onshore) | Asyraf |  |  | Ali | Weather limit
Non-Offshore | 0% |  | 2026-09-15 | onshore | WOW(onshore) | Asyraf | Fremmy | Aiman | Ali | Training
Non-Offshore | 0% |  | 2026-09-16 | onshore | WOW(onshore) | Asyraf | Fremmy | Aiman | Ali | Training
D06 | 0% | 1 | 2026-09-17 | offshore | WOW(offshore) | Asyraf | Fremmy | Aiman | Ali | Strong current. CTV turned back before entering the F2 wind farm.
D05 | 0% | 3 | 2026-09-18 | offshore | WOW(offshore) | Asyraf | Fremmy | Aiman | Ali | Strong current. CTV unable to push on
C09 | 10% | 1 | 2026-09-19 | offshore | Inspection | Asyraf | Fremmy | Aiman | David
C09 | 22% | 1 | 2026-09-20 | offshore | Inspection | Asyraf | Fremmy | Aiman | David | Due to worsening weather, we came down from the tower at around 11:00. The Tetherline was damaged during AIB launch and was replaced with a spare.
C09 | 22% | 1 | 2026-09-21 | offshore | WOW(offshore) | Asyraf | Fremmy | Aiman | David | Strong current. CTV unable to push on
C09 | 22% | 1 | 2026-09-22 | offshore | WOW(offshore) | Asyraf | Fremmy | Aiman | Ali | Strong current. CTV turned back before entering the F2 wind farm.
Non-Offshore | 0% |  | 2026-09-23 | onshore | Delay | Asyraf |  |  | Ali | Power outage on the wind farm
C09 | 22% | 1 | 2026-09-24 | offshore | Inspection | Asyraf | Fremmy | Aiman | Michael | Power outage on the wind farm
D05 | 14% | 3 | 2026-09-25 | offshore | Inspection | Asyraf/Aiman | Fremmy/Zaidi | Ali/Michael
D05 | 31% | 3 | 2026-09-26 | offshore | Inspection | Asyraf/Aiman | Fremmy/Zaidi | David/Michael |  | Fishnets found at A3B, C3D, D2C. A keychain found at D2C.
D05 | 45% | 3 | 2026-09-27 | offshore | Inspection | Asyraf/Aiman | Fremmy/Zaidi | Michael |  | Strong surface current pushed the AIB into the jacket near Leg C, causing tether entanglement.
C09 | 44% | 1 | 2026-09-28 | offshore | Inspection | Aiman | Fremmy | Ali
D05 | 55% | 3 | 2026-09-28 | offshore | Inspection | Asyraf | Zaidi | Michael
C09 | 71% | 1 | 2026-09-29 | offshore | Inspection | Aiman | Fremmy | Ali
D05 | 76% | 3 | 2026-09-29 | offshore | Inspection | Asyraf | Zaidi | Michael
C09 | 100% | 1 | 2026-09-30 | offshore | Inspection | Aiman | Fremmy | Ali
D05 | 100% | 3 | 2026-10-01 | offshore | Inspection | Asyraf | Zaidi | Ali |  | Fishing net entangled with thrusters 2, 4, and 6 (resolved).
D12 | 0% | 1 | 2026-10-02 | offshore | WOW(offshore) | Asyraf | Zaidi | Michael |  | High current. CTV unable to push on.
D08 | 0% | 2 | 2026-10-02 | offshore | WOW(offshore) | Aiman | Fremmy | Ali |  | High current. CTV unable to push on.
Non-Offshore | 0% |  | 2026-10-03 | onshore | WOW(onshore) | Asyraf/Aiman | Fremmy/Zaidi | Ali/Michael |  | Weather limit
Non-Offshore | 0% |  | 2026-10-04 | onshore | WOW(onshore) | Asyraf/Aiman | Fremmy/Zaidi | Ali/Michael |  | Weather limit
Non-Offshore | 0% |  | 2026-10-05 | onshore | WOW(onshore) | Asyraf/Aiman | Fremmy/Zaidi | Ali/Michael |  | Weather limit
Non-Offshore | 0% |  | 2026-10-06 | onshore | WOW(onshore) | Asyraf/Aiman | Fremmy/Zaidi | Ali/Michael |  | Weather limit
Non-Offshore | 0% |  | 2026-10-07 | onshore | WOW(onshore) | Asyraf/Aiman | Fremmy/Zaidi | Ali/Michael |  | Weather limit
Non-Offshore | 0% |  | 2026-10-08 | onshore | Day off |  |  | Ali/Michael |  | Day off(IOG)
Non-Offshore | 0% |  | 2026-10-09 | onshore | Day off |  |  | Ali/Michael |  | Day off(IOG)
Non-Offshore | 0% |  | 2026-10-10 | onshore | Day off |  |  | Ali/Michael |  | Day off(IOG)
Non-Offshore | 0% |  | 2026-10-11 | onshore | Day off |  |  | Ali/Michael |  | Day off(IOG)
Non-Offshore | 0% |  | 2026-10-12 | onshore | Day off |  |  | Ali/Michael |  | Day off(IOG)
D12 | 100% | 1 | 2026-10-13 | offshore | Inspection | Aiman | Fremmy | Ali |  | Continued last year's MGM inspection at D12 Leg A
D08 | 100% | 2 | 2026-10-13 | offshore | Inspection | Dil | Shafiq | Zaidi | Michael | Continued last year's MGM inspection at D08 Leg A
Non-Offshore | 0% |  | 2026-10-14 | onshore | WOW(onshore) | Dil/Aiman | Fremmy/Zaidi/Shafiq | Ali/Michael |  | Weather limit
Non-Offshore | 0% |  | 2026-10-15 | onshore | WOW(onshore) | Dil/Aiman | Fremmy/Zaidi/Shafiq | Ali/Michael |  | Weather limit
A06 | 75% | 5 | 2026-10-16 | offshore | Inspection | Dil | Aiman | Fremmy | Ali | Continuation of last year's work / Unable to commence operations due to crane issue.
C01 | 100% | 4 | 2026-10-16 | offshore | Inspection | Shafiq | Zaidi | Michael |  | Continuation of last year's work
D06 | 0% | 2 | 2026-10-17 | offshore | Inspection | Aiman | Fremmy | Ali |  | 1. Strong currents – Waiting on Weather. 2.No power supply at TP – Move to another jacket tomorrow.
D04 | 0% | 2 | 2026-10-17 | offshore | Inspection | Shafiq | Zaidi | Michael |  | Unable to climb the tower due to an SRL issue. Switched to D01.
D01 | 0% | 2 | 2026-10-17 | offshore | Inspection | Shafiq | Zaidi | Michael |  | Strong currents – Waiting on Weather.
D01 |  | 2 | 2026-10-18 | offshore | Inspection | Shafiq | Zaidi | Michael
C10 | 0% | 2 | 2026-10-18 | offshore | Inspection | Aiman | Fremmy | Ali |  | 1.Assisted Siemens technicians with SRL replacement during work at height. 2. Strong currents – Waiting on Weather.